EduBoost V2
Final Technical Assessment and Release Packet

Repository-level backend consolidation through slices 530/530

Prepared for: EduBoost V2 release-owner review

Basis: user-provided execution status and branch synchronization confirmation through final backend consolidation batches.

Classification note: This packet classifies repository-level completion. Production launch remains pending external runtime evidence and human approvals.

# 1. Executive Technical Assessment

EduBoost V2 backend consolidation has reached repository-level implementation completion for the consolidation runway. The project has progressed from diagnostics and safety scaffolding into runtime-facing implementation across audit, consent, read-only deep readiness, disposable DB schema-proof tooling, and cleanup readiness.

| Repository implementation | GREEN, based on user-provided final status. |
| --- | --- |
| Backend consolidation runway | COMPLETE through slices 530/530. |
| Production launch | PENDING external runtime evidence and human signoff. |
| Recommended posture | Conditional GO for evidence execution; NO-GO for production launch until remaining evidence is complete. |

# 2. Technical State

| Layer | State | Technical meaning |
| --- | --- | --- |
| Diagnostic | Complete | Audit/consent call-site inventories and dragon mapping established. |
| Compatibility | Complete | Audit adapter, consent normalizers, and runtime facades exist. |
| Runtime implementation | Implemented | First audit runtime integration, consent runtime repair, and read-only deep readiness service exist. |
| Environment proof | Tooling complete | Disposable DB proof can execute when a safe DATABASE_URL is provided. |
| Cleanup | Ready | Conservative post-migration cleanup tooling exists. |
| Governance | Ready | Evidence index, terminal reports, checklists, and go/no-go templates exist. |

# 3. Production-Readiness Status

| Category | Status | Required next action |
| --- | --- | --- |
| Local tests | Green per user confirmation | Refresh and archive final output. |
| Remote CI | Pending evidence | Capture workflow URL and results. |
| Disposable DB schema proof | Pending real DB execution | Run proof against disposable PostgreSQL only. |
| Staging smoke | Pending real staging URL | Run staging smoke and archive JSON/text output. |
| Backup/restore drill | Pending | Execute and archive drill evidence. |
| Rollback drill | Pending | Execute and archive rollback evidence. |
| Security/POPIA/legal review | Pending | Complete human review and signoff. |
| Release-owner go/no-go | Pending | Sign final production decision memo. |

# 4. Remaining External Evidence Checklist

| Priority | Evidence item | Completion criterion |
| --- | --- | --- |
| P0 | Final local evidence refresh | Full test output committed after final push. |
| P1 | Remote CI | Green GitHub Actions run URL archived. |
| P2 | Disposable DB proof | Schema proof and ORM-vs-DB comparison pass. |
| P3 | Staging smoke | Real staging smoke passes. |
| P4 | Operational drills | Backup/restore and rollback drills pass. |
| P5 | Human approvals | Security, POPIA, legal, CAPS/content, and release-owner approvals captured. |

# 5. Release-Owner Go/No-Go Memo

| Current recommendation | CONDITIONAL GO for production-readiness evidence execution. |
| --- | --- |
| Production launch decision | NO-GO until external evidence and human approvals are complete. |
| Why not full GO yet | Repository-level completion does not prove staging/prod runtime behavior, operational drills, or legal/security approval. |
| Explicit non-approvals | No approval to drop audit_logs, merge consent tables, delete history, stamp Alembic head, mutate production DB outside migration window, or add public mutating health probes. |

# 6. Updated North-Star Execution List

North Star: Ship a production-capable EduBoost V2 backend by converting repository-level completion into external runtime evidence, release-owner approval, and controlled production deployment.

| Phase | Task group | Status |
| --- | --- | --- |
| P0 | Freeze and evidence refresh | Pending |
| P1 | Remote CI evidence | Pending |
| P2 | Disposable DB proof | Pending |
| P3 | Staging smoke | Pending |
| P4 | Operational drills | Pending |
| P5 | Human approvals | Pending |
| P6 | Controlled production deployment | Blocked until P0-P5 complete |

# 7. Final Classification

| Repository implementation | GREEN |
| --- | --- |
| Backend consolidation | COMPLETE |
| Production-readiness evidence | PARTIAL; external evidence pending |
| Production launch | NO-GO until external evidence and human approval gates pass |

Evidence discipline: This packet is intentionally conservative: unsupported launch claims remain blockers until external evidence is attached.